CUTLER-OROSI UNIFIED SCHOOL DISTRICT

TIMELINE FOR REDISTRICTING TRUSTEE AREAS

(Note:  most actions are goal dates subject to change.

Only items in bold are fixed deadlines.)

| DATE | ACTION |
| --- | --- |
| August 12, 2021 Board Meeting | Board adopts tentative calendar for redistricting; approves contract for demographic consultant. |
| August 16, 2021 | Announced date for federal government to release “legacy format” demographic/redistricting data to States. (In a normal post-Census year, the data would have been released by Mar. 31.) |
| September 9, 2021 Board Meeting | Presentations at Board meeting re legal criteria governing redistricting and demographics of current trustee areas. Receive public comment. Board provides instructions for the preparation of alternative draft redistricting plans. |
| End of September | Three initial draft trustee area plans (or more if the Board so instructs) to be made publicly available (posted on District’s website for public consideration and made available at the District’s administrative offices). |
| October 14, 2021 Board Meeting | Demographic consultant to present initial draft trustee area plans; Board solicits public testimony on draft plans. |
| Late-October – early Nov. 2021 | OPTIONAL: Informational meeting to solicit public comment regarding draft plans. |
| October 25, 2022 | Notice of first public hearing published in a newspaper of general circulation and posted online and in other locations where notices are typically posted. |
| Nov. 4, 2021 Board Meeting | Board holds first public hearing on alternate plans; Board may order modifications to any of the plans. |
| January 3, 2022 | Notice of second public hearing published in a newspaper of general circulation and posted online and in other locations where notices are typically posted. |
| January 13, 2022 Board Meeting | Board holds second public hearing on alternate plans, votes to choose one plan. If Board orders further modifications, another public hearing will be necessary in February. |
| February 2022 Board Meeting | Last Board meeting prior to legal deadline |
| February 28, 2022 | Legal Deadline to complete adjustment of trustee areas. |
| July 18, 2022 | First day for circulating nomination papers. |
| November 8, 2022 | Election using new trustee area plan. |